Sean McCarthy limited

Trading as McCarthy Piling

24 Den Hill Drive

Springfield

Oldham

OL4 4NR

Company Number: 07948562

Vat Reg Number: 132542149

Village Homes ( Folkestone) Ltd

2 The Glenmore Centre

Shearway Business Park

Pent Road

Folkestone

Kent

CT20 3NN

Quote Ref: ADC/1077/220121

Friday 22nd January 2021

For the Attention of Mr Kevin O’Connor

Dear Kevin

Re: Land adjacent to Romney Avenue, Folkestone, Kent, CT20 3QJ

We thank you for your recent telephone conversation and email correspondence in relation to the above named project.

We are pleased to offer you our budget quotation based on the information provided below:

Permanent Retaining Wall based on 54 Linear Metres ( with retained height varying from 1.5 metres to 4 metres maximum ( note 4 metre maximum after telephone conversation with Kevin 22.01.21 explaining this MUST be the maximum retained height)

INSTALLATION

VISIT 1

- Preliminaries, work method statement, risk assessment, lift plans

( design by others)

2,495.00

- Supply of Steel Sheet Piles:

( if required to be supplied by McCarthy Piling)

ALL GU21N piles:

16nr @ 5 metres long

8nr @ 6 metres long

4nr @ 8 metres long

21nr @ 9 metres long

4nr @ 10 metres long

8nr @ 11 metres long

29nr @ 12 metres long

All piles will be provided at lengths and section mentioned above

( or similar subject to FULL design calculation package)

53,500.00

Due to value of piles, we would require £ 26,750.00 + VAT to be

Paid upfront at point of ordering the piles, with the remaining

Balance of the pile value, to be invoiced when all piles are on

Site with  strict 30 day payment terms

- Handle/Pitch/Drive steel sheet  piles as stipulated

Above to Level/refusal utilising 35 Tonne Excavator with Movax

Attachment

9,495.00

( Noise /Vibration Methodology )

Estimated programme based on working weekdays Monday –

Friday 0730-1800hrs – 4 working days

- Demobilisation and clear site                                                 1,995.00

Total Installation Costs  = £ 67,485.00

Potential Additional Installation Costs:

- Design Calculation package ( if required to be undertaken by McCarthy Piling)

£ 4,345.00

- Pre Augering of Pile Line ( if required) - £ 7,495.00 – estimated programme 3 working days

- Impact Driving of Piles to level/refusal ( if required) utilsing DH20 Impact Hammer –

£ 9,995.00

Estimated programme 3 working days

- Any standing time charged @ £210.00 per hour – Movax/Auger Gang

Any standing time charged @ £250.00 per hour – when Impact Hammer is on site

Terms and Conditions:

- The above   quotation has been based on information provided within the quotation is subject to revision upon completion of a site visit, based on driving piles from a level of approximately 41m AOD in relation to Borehole Logs BH1 and BH2 and  production of design calculations and CONSTRUCTION ISSUE drawings.

It must be stressed that this is a budget quotation only and ‘best guess ‘ re pile section /lengths required based on the information provided but accurate design calculations will determine the true pile lengths/sections.

Our quotation is based on noise and vibration (Should lighting be required , it is the responsibility of the client to provide such.

.

b) We have assumed that you will provide clear and unrestricted access to and from site at all times, diversion or removal of all overhead and underground services or obstructions prior to commencement of piling.

c) Provision of all necessary accurate setting out and clear/robust marking or exposing on site the exact underground/overhead services is to be met by the Main Contractor along with providing a drawing on their positions in line and level to ensure relevance to Sean McCarthy Limited's work.

d) Protection ,diversion or removal of such services is also required by the Main Contractor to prevent damage from Sean McCarthy Limited works.

e) A permit to dig or similar system is to be used to Sean McCarthy Limited on a daily/or otherwise agreed basis PRIOR to the commencement of our works.

f) Prior removal of overhead, surface or underground obstructions which may impede the works and backfilling of excavations and voids with suitable material which will not obstruct or be detremental to the works but will ensure the stability of Sean McCarthy Limited's work.

g) Provision of ROBUST security to safeguard the plant, equipment and materials on site is the responsibility of the Main Contractor.

h) Design, installation, maintenance, and repair of a suitable working platform is the responsibility of the Main Contractor and if necessary provide a signed copy of the working platform certificate before commencement of any works to ensure adequate ground bearing capacity for our plant/equipment.

i) McCarthy Piling can accept NO responsibility to damage of piles during the installation  /extraction process due to driveability/site ground conditions or otherwise

j) The piles are subject to availability and price at the time of any order. All piles supplied are deemed to be new or good pre used from stock holder remaining unsold.

k) We wish to confirm that due to fluctuations in current steel prices, this quotation can only be fixed for 10 days from the date of this letter. We require PAYMENT of Piles upon delivery as materials on site.

l) The legal ownership of and title in all permanent materials supplied shall remain with ourselves and not pass including the full right of disposal until we have received payment in full EXCLUDING retention.

m) The measurement of any item for which our quoted rate includes for handling , pitching and driving piles and shall be based on the area/length pitched whether driven to the required level or to prior practical refusal as defined in these conditions.

n) Where pre augering is required, an attendant excavator will be required ( provided by the Main Contractor) for the clearing and levelling of generated spoil.

o) In the event of difficult driving or of encountering obstructions or other physical conditions which obstruct , deflect or otherwise impede the penetration of piles to design depth/progress on site, we shall be entitled standing time pending an agreed method of proceeding. All extra costs incurred in consequence of such matters including the costs of any materially altered method of driving or any special or substantially more expensive or more protracted method of driving will be charged to the client.

p) Piles will be driven to within 50mm of agreed levels or refusal, whichever occurs first, REFUSAL being deemed as one of the following:

a) 10 blows of the specified hammer for 25mm of penetration

b) 1 minute of continual driving with the specified vibratory hammer fails to achieve 75 mm of penetration.

( The client is free to inspect every pile as it is being driven).

c) Distortion occurs to the pile head.

Should we be instructed to bring to site more powerful and/or more expensive equipment to site, for driving, all associated costs will be borne by the Client.

q) Piling by it's very nature can be noisy and give rise to vibration. We take all reasonable steps to minimise nuisance and damage but can accept no liability in this connection. We have made no allowance for the use of specialist equipment with regard to noise and/or vibration, except where stated otherwise.

r) We accept no responsibility should piles be deflected, moved, declutched, drawn down, bent or distorted out of line or otherwise fail to achieve design due to ground conditions whether foreseeable or not.

s) During installation and extraction of piles there can be a tendency for settlement to occur adjacent to the pile line as the work improves the density of adjacent soils. We do not accept liability or the like resulting from this effect.

t) Inflows of water can be expected in cofferdams. or retaining walls, below the water table. All costs incurred in dealing with the ingress of water are the responsibility of the Main Contractor.

u) No deduction of money by way of retention shall be allowed in sheet piling works.

v) No deduction of monies or 'set off' against payments due will be allowed without our written agreement.

w) The total amount of any damages ( liquidated and/or ascertained) will be NIL.

x) No allowance has been made in our tender price for the provision of a performance bond ,deed, or a collateral warranty.

y) Where piles are to be driven to ground or cut level, if below, then a lead trench will be required ( excavated by the Main Contractor) to enable the specified equipment to operate below ground level.

z) Site Record Sheets detailing events and resources on site will be submitted daily at site level for agreement and signature.

1) Burning off to within 25mm of given level, a minimum of 250mm above water level.

Except where deflected by obstructions or varying ground conditions, we shall endeavour to drive piles to within the following tolerances:

+/- 75MM of the given line at commencing level

1:75 of verticality for vertical piles

1:25 of design rake for raking piles

50mm of the required level ( unless prior refusal is reached)

2) Piles supplied by Sean McCarthy Limited and/or the Main/Principal Contractor will be supplied in accordance with the pile manufacturers rolling  tolerances.

3) Sheet piles deflect to an indeterminate degree which may result in settlement or subsistence for which we accept no liability. This should be closely monitored and should be resolved before becoming aggressive, by the Main Contractor.

4) Sheet Piling has a limited range of stability. Should the piles be subject to increased loading or over- excavation this may lead to instability , we can accept no liability should this occur.

A full method statement, risk assessment and lift plan will be provided upon receipt of an official order.( for Option1 – Contract Price Only)

VAT is to be charged at the standard rate to all  the above rates

Our terms of payment are to be nett within 30 days of our applications. If payments are not made in accordance with the above terms/agreed contract, interest shall be chargeable at 2% per month thereafter on the amount(s) overdue.

This quotation is valid for 30 days.

Yours Faithfully

Andy Clay

Contracts and Operations Director